## Sheet1
Week | Building CICD Pipeline | Difficulty
2022-10-28 | Create spreadsheet of project plan | Easy
2022-10-28 | Create trello board | Easy
2022-10-28 | Create Git repo | Easy
2022-10-29 | Replace the scaffolding code with the flask code | Easy
2022-10-29 | Ensure the app runs locally without errors | Medium
2022-10-29 | Ensure the app runs in Cloud Shell without errors | Medium
2022-10-29 | Set up GitHub Actions | Hard
2022-10-29 | Add the GitHub Actions badge to the README | Medium
2022-10-29 | Create the App Service in Azure | Medium
2022-10-29 | Test the app running in Azure App Service | Medium
2022-10-30 | Set up the Azure DevOps pipeline | Hard
2022-10-30 | Create architectural diagram | Medium
2022-10-30 | Take screenshots demonstrating key steps | Easy
2022-10-30 | Create README file with full instructions of how to run the code | Easy
2022-10-30 | Create demo video and post to YouTube | Medium
| Goals | Goals
Deploy flask app using CICD pipeline sucessfully
Q4 plan | Deploy flask app using CICD pipeline sucessfully and Submit the project
Yearly plan | Review the code and ensure it still works